WEEK 01  |  PROJECT PLANNING

# Apparel & Textiles
E-Commerce Website

Project strategy, delivery roadmap and risk framework

| PROJECT TYPE | Responsive e-commerce planning |
| --- | --- |
| PLANNED DELIVERY | 8-week MVP roadmap |
| PREPARED BY | [Enter your full name] |

PROJECT INTENT

Plan a practical digital storefront that makes apparel and textile products easier to discover, understand, purchase and manage—while keeping stock information, checkout, delivery communication and customer trust at the centre.

# 01  |  Executive brief

This proposal defines a phased plan for a mobile-first website selling apparel and textile products. The platform is intended to connect compelling product presentation with dependable commerce operations: accurate variant-level stock, clear material and size information, secure checkout, order updates, and a manageable back-office workflow. The recommended approach is to launch a focused minimum viable product (MVP), validate it with users, then add advanced capabilities only when evidence and budget justify them.

| CUSTOMER VALUE Clear product details + easy shopping | OPERATIONS VALUE Variant stock + order visibility | DELIVERY APPROACH 8-week MVP, then measured iteration |
| --- | --- | --- |

# 02  |  Objectives and success measures

Provide a responsive shopping experience across mobile, tablet and desktop.

Show product photography, fabric composition, colour/size variants, measurements, care instructions and current availability.

Track stock by SKU and variant to reduce overselling and manual reconciliation.

Offer a short, secure checkout with clear shipping fees, delivery expectations, payment status and order confirmation.

Build customer confidence through accessible return, exchange, privacy and contact information.

Use analytics and customer feedback to improve product discovery, conversion and post-purchase service.

Measurement approach: establish a baseline after launch, then agree realistic targets with the business owner for conversion, cart abandonment, stock accuracy, page performance, return reasons and customer satisfaction. Targets should not be invented before baseline data exists.

# 03  |  Audience and user needs

| AUDIENCE | PRIMARY NEED | DESIGN RESPONSE |
| --- | --- | --- |
| Everyday apparel shoppers | Find suitable styles, sizes, prices and delivery details quickly. | Visual categories, filters, size guide and clear delivery information. |
| Fabric and textile buyers | Understand composition, width, texture, colour and care. | Fabric specifications, close-up imagery and consistent product attributes. |
| Boutiques, tailors and resellers | Check availability and ask about larger/repeat quantities. | SKU-level stock, bulk enquiry form and contact route. |
| Mobile-first/social visitors | Open a product page quickly and trust the seller. | Fast responsive pages, shareable product links and visible policies. |

# 04  |  Industry signals and product implications

Public research supports a practical rather than feature-heavy strategy:

DHL’s 2025 global e-commerce shopper study surveyed 24,000 shoppers across 24 markets. It reports that missing preferred delivery options are a major reason for cart abandonment, and highlights social commerce, sustainability and AI-enabled shopping as important trends. For this project, delivery information and mobile-friendly product sharing should be prioritized before expensive AI features. [1]

KPMG India’s 2025 apparel customer-experience analysis identifies smooth checkout, multiple payment methods, clear return/refund policies, customer support and efficient exchanges as important experience factors. The website should make these details easy to find before and after purchase. [2]

Visual quality matters in apparel, but product images should be paired with factual information: measurements, fabric composition, fit notes, care instructions and stock status. This reduces uncertainty that photos alone cannot resolve.

Sustainability claims should be specific and verifiable. Avoid broad claims such as “eco-friendly” unless evidence supports them; where available, show material sourcing, certifications, packaging details or care advice.

Strategic decision: launch with reliable catalogue, inventory, checkout and service information. Add loyalty, personalization, virtual try-on or AI-assisted discovery only after the core shopping journey works consistently.

# 05  |  Competitor review

This is a qualitative review of publicly visible storefront features, not an assessment of competitors’ private revenue, conversion or internal technology.

| REFERENCE | PUBLICLY VISIBLE APPROACH | LESSON FOR THIS PROJECT | PUBLIC SOURCE |
| --- | --- | --- | --- |
| H&M India | Digital membership, points, offers and sale access. | Consider loyalty as a later retention feature; first ensure useful product details and stock accuracy. | Official membership page [3] |
| Zara | Collection-led browsing and strong visual merchandising. | Use consistent product imagery and simple navigation without hiding price, material or return information. | Official India storefront [4] |
| Myntra | Broad fashion discovery across brands, categories, filters and offers. | A focused apparel/textile store can differentiate through richer fabric specifications, clear variant availability and direct brand storytelling. | Official website [5] |
| KPMG apparel CX benchmark | Research highlights checkout, payments, returns/exchanges and support. | Treat service design as part of the product, not an afterthought. | KPMG India report [2] |

Opportunity statement: a smaller store is unlikely to match large marketplaces on catalogue size. It can compete through a clearly defined niche, dependable information, accurate inventory, helpful service and a low-friction buying journey.

# 06  |  Scope and deliverables

## MVP: included

Home page with categories, featured collections and seasonal/promotional banners.

Product listing pages with search, sorting and relevant filters (category, price, size, colour, material).

Product detail pages with multiple images, price, SKU, variant selector, fabric composition, measurements, care instructions, availability and delivery/return summary.

Shopping cart, checkout, customer and delivery details, payment gateway integration, order confirmation and order history.

Admin functions to create/update products, manage variants and stock, view low-stock items, process orders and update fulfilment status.

FAQ, contact/support form, shipping policy, return/exchange policy, privacy notice and terms.

Responsive layout, accessible forms, search-engine metadata, analytics, error logging and backups.

## Later release candidates

Wishlist, verified reviews, loyalty points, multilingual content, personalized recommendations, live chat, wholesale pricing, social-commerce integrations and advanced forecasting. Each should be prioritized through user feedback and cost-benefit review.

## Out of scope for MVP

Building a custom payment network, native mobile apps, manufacturing-planning software or a full enterprise resource-planning system from scratch.

# 07  |  Requirements and acceptance checks

| ID | REQUIREMENT | ACCEPTANCE CHECK |
| --- | --- | --- |
| F-01 Catalogue | Admin manages products, categories, images, prices, SKUs and variants. | A product can be created, edited and shown correctly on the storefront. |
| F-02 Discovery | Search and filters help users narrow the catalogue. | A tester can find a product by keyword and filter available attributes. |
| F-03 Inventory | Stock is maintained for each size/colour/fabric variant where applicable. | A confirmed order updates stock and unavailable variants cannot be ordered. |
| F-04 Checkout | Cart totals, delivery details, payment and confirmation work end to end. | Test orders cover success, failure and cancelled payment paths. |
| F-05 Orders | Customers see order confirmation; admins update order/fulfilment status. | Order status is consistent in admin and customer views. |
| F-06 Service | Policies and contact/support options are easy to find. | Tester locates delivery, returns and contact details without assistance. |
| NF-01 Security | HTTPS, protected admin access, validation and safe secret handling. | No raw payment-card details are stored; access roles are tested. |
| NF-02 Performance | Optimized images, limited scripts and mobile testing. | Core pages remain usable on common mobile screen sizes and slower connections. |
| NF-03 Accessibility | Readable contrast, labels, alt text and keyboard navigation. | Forms and navigation can be used without relying only on a mouse. |
| NF-04 Recovery | Backups, monitoring and restoration process. | A test backup can be restored in a controlled environment. |

# 08  |  Technical approach and data design

Use a supported, maintainable stack chosen for the team’s skills and hosting budget. A reasonable custom-build option is HTML/CSS/JavaScript for the responsive interface, a backend such as Django, Flask or Laravel, and a relational database such as PostgreSQL or MySQL. A hosted commerce platform is also valid if it meets customization, cost and integration needs. The final choice should be made after comparing total cost, payment/shipping support, security maintenance and expected catalogue size.

Core data entities: Product, Category, ProductVariant/SKU, Inventory, Customer, Address, Cart, Order, OrderItem, PaymentReference, Shipment, Review and Promotion. Validate inventory and order/payment state on the server; use a trusted payment provider and do not store raw card details. Keep API keys and passwords out of source control.

# 09  |  Delivery roadmap and milestones

| WHEN | PHASE | KEY WORK | MILESTONE / EVIDENCE |
| --- | --- | --- | --- |
| Week 1 | Discovery and planning | Confirm goals, audience, MVP, risks, competitor observations and success measures. | Approved plan and scope. |
| Week 2 | Requirements and content | User stories, site map, product data template, policies and content checklist. | Requirements sign-off. |
| Week 3 | UX/UI design | Wireframes, mobile layouts, catalogue/product-page prototypes and review. | Approved design prototype. |
| Weeks 4–5 | Core development | Catalogue, search/filter, product pages, database and inventory admin. | Working catalogue and admin demo. |
| Week 6 | Commerce integration | Cart, checkout, payment sandbox, order confirmation and order management. | Successful end-to-end test order. |
| Week 7 | QA and security | Functional, mobile, accessibility, permissions, performance, backup and failure-path tests. | Test report; critical defects resolved. |
| Week 8 | Launch preparation | Production configuration, HTTPS, analytics, content checks, staff walkthrough and rollback plan. | Go-live checklist approved. |
| Post-launch | Measure and improve | Review analytics, support issues, stock accuracy and user feedback. | 30-day improvement backlog. |

Schedule assumption: one small cross-functional team and prompt business approvals. Delays in product photography, SKU cleanup, payment onboarding or policy decisions may extend the schedule.

# 10  |  Resource allocation

| ROLE | INDICATIVE INVOLVEMENT | ACCOUNTABILITY |
| --- | --- | --- |
| Project/business owner | 10–15% throughout | Priorities, approvals, scope, budget and acceptance. |
| UX/UI designer | 20–30% in Weeks 2–3 | User journeys, responsive screens and accessibility review. |
| Frontend developer | Main build period | Storefront, responsive layouts, forms, cart experience. |
| Backend developer | Main build period | Database, APIs, inventory, authentication and integrations. |
| QA tester | Part-time; intensive in Week 7 | Test cases, regression checks, compatibility and defect reports. |
| Catalogue/content owner | Part-time throughout | Product images, SKUs, descriptions, size charts, stock and policies. |
| Hosting/payment/shipping providers | As needed | Infrastructure, payment processing and fulfilment services. |

For a student project, one person may cover several roles. These percentages are planning estimates rather than fixed staffing commitments. Use version control, a task board, weekly reviews and written acceptance criteria.

# 11  |  Risk register and response plan

| RISK | PRIORITY | PREVENTION / MITIGATION | EARLY WARNING |
| --- | --- | --- | --- |
| Incorrect stock / overselling | High | Unique SKU per variant; server-side stock checks; controlled stock updates; regular reconciliation. | Negative stock, cancelled orders or frequent discrepancies. |
| Security or account compromise | High | HTTPS, least-privilege roles, strong admin authentication, dependency updates, logging and backups. | Unusual logins, repeated failures or unexpected admin changes. |
| Slow or confusing mobile experience | High | Mobile-first design, image compression, limited scripts, real-device testing and performance monitoring. | Slow product pages or high mobile abandonment. |
| Returns caused by unclear product details | Medium–High | Accurate measurements, material/care details, colour photos, fit notes and visible return rules. | Repeated size/material complaints. |
| Delivery delays or unclear costs | High | Show delivery estimate and fees early; confirm serviceable areas; provide order updates and escalation path. | Support contacts about delivery or abandoned checkout. |
| Scope creep / missed deadline | Medium | Freeze MVP; prioritize backlog; approve changes formally; reserve contingency time. | New features added without trade-offs. |
| Traffic or database spike | Medium | Scalable hosting, suitable indexes/caching, monitoring and load tests for critical journeys. | Rising response times or server errors. |
| Privacy incident or data loss | High | Collect only necessary data; restrict access; maintain encrypted backups and test restoration. | Failed backups or unauthorized access alerts. |
| Low engagement after launch | Medium | Measure search terms and funnels; gather feedback; improve content, SEO and relevant opt-in communications. | Low product engagement or repeat visits. |

Risk review cadence: review the register at the end of each project week and immediately after a serious incident. Assign a named owner to each high-priority risk before development begins.

# 12  |  Testing, launch and ongoing improvement

Functional tests: search, filters, variant selection, cart totals, checkout success/failure, stock updates, order status and admin permissions.

Usability checks: ask representative users to find a product, understand its material/size, complete a test order and locate the return policy.

Compatibility and accessibility: test major browsers, mobile sizes, keyboard navigation, contrast, form labels and image descriptions.

Security and recovery: verify HTTPS, access controls, input validation, secret management, dependency updates and backup restoration.

Launch readiness: production content verified, policies reviewed, analytics enabled, support contact tested, database backed up and rollback steps documented.

Post-launch review: inspect errors and stock exceptions weekly at first; review conversion, returns, support response and customer feedback monthly.

# 13  |  KPIs and go-live decision

| MEASURE | WHY IT MATTERS | REVIEW |
| --- | --- | --- |
| Product discovery and search usage | Shows whether customers can find relevant items. | Weekly after launch |
| Add-to-cart and checkout completion | Identifies friction in the buying journey. | Weekly / monthly trend |
| Stock accuracy and cancellation rate | Checks operational reliability. | Weekly |
| Page performance and error rate | Protects usability and trust. | Weekly |
| Return reasons and support response time | Reveals product-information and service gaps. | Monthly |
| Repeat visits and customer feedback | Indicates engagement and opportunities to improve. | Monthly |

Go-live gate: launch only when critical user journeys work, no critical/high-severity defects remain open, stock and payment failure cases have been tested, policy content is approved, backups are verified, and an owner is assigned to monitor issues.

# 14  |  Conclusion

The proposed website should succeed by combining visual appeal with operational accuracy and customer trust. The eight-week roadmap prioritizes the features that directly support product discovery, variant-level inventory, secure checkout, delivery communication and after-sales support. Competitor observations and published industry research inform the strategy, while explicit milestones, acceptance checks and risk responses make the plan measurable. Advanced features are intentionally deferred until the core experience is stable and customer evidence supports further investment.

# 15  |  References

[1] DHL Group (4 June 2025), “DHL’s E-Commerce Trends Report 2025: AI and social media reshaping online shopping.”

[2] KPMG India, “India CX Report ’25: Apparel.”

[3] H&M India, “H&M Membership.”

[4] Zara India, official storefront.

[5] Myntra, official website.

Source note: competitor observations reflect public-facing pages reviewed for planning and may change. Industry findings apply to the surveys and markets described by the publishers; they are contextual evidence, not guaranteed outcomes for this proposed website.